Please select the valid Estimation type
Please select the Estimation type
## Summary
IVTL_Commuting Costs (Employee Info)
	Analysis					Estimation Type
S. No	Task			Total Hours	Man Days	Man Months	Start Date	End Date			NEW
1	Catalog and Design			136.00	17.00	0.85	06/12/2017	07/05/2017
	Development
S. No	Task	Total Components	Checkpoint	Total Hours	Man Days	Man Months	Start Date	End Date
1	0	190	0	414.60	51.83	2.59
2	0	0	0	0.00	0.00	0.00
3	0	0	0	0.00	0.00	0.00
4	0	0	0	0.00	0.00	0.00
5	0	0	0	0.00	0.00	0.00
6	0	0	0	0.00	0.00	0.00
7	0	0	0	0.00	0.00	0.00
8	0	0	0	0.00	0.00	0.00
9	0	0	0	0.00	0.00	0.00
10	0	0	0	0.00	0.00	0.00
	Total	190		414.60	51.83	2.59	07/06/2017	07/31/2017
	Unit Testing
S. No	Task			Total Hours	Man Days	Man Months	Start Date	End Date
1	Unit Testing			0.00	0.00	0.00	07/31/2017	07/31/2017
	Code Review
S. No	Task			Total Hours	Man Days	Man Months	Start Date	End Date
1	Testing
1	Code Review			16.00	2.00	0.10	08/01/2017	08/02/2017
	Total				0.00	0.00
	Hyouka
S. No	Task			Total Hours	Man Days	Man Months	Start Date	End Date
1	Testing
1	Catalog Analysis and Test case preparation			40.00	5.00	0.25	07/06/2017	07/12/2017
S. No	Task		Checkpoint	Total Hours	Man Days	Man Months	Start Date	End Date
1	0		0	103.65	12.96	0.65
2	0		0	0.00	0.00	0.00
3	0		0	0.00	0.00	0.00
4	0		0	0.00	0.00	0.00
5	0		0	0.00	0.00	0.00
6	0		0	0.00	0.00	0.00
7	0		0	0.00	0.00	0.00
8	0		0	0.00	0.00	0.00
9	0		0	0.00	0.00	0.00
10	0		0	0.00	0.00	0.00
2	Chennai – Hyouka			103.65	12.96	0.65	08/03/2017	08/30/2017
3	Support			103.65	12.96	0.65	08/03/2017	08/30/2017

Total				813.90	101.74	5.09	06/12/2017	08/30/2017

## Estimation
IVTL_Commuting Costs (Employee Info)
S. No	Component and Description	Screen / 1	Screen 2	Screen 3	Screen 4	Screen 5	Screen 6	Screen 7	Screen 8	Screen 9	Screen 10	Total (Hrs)	Total (Days)	Total (Months)					m1	m2	m3	m4	m5	m6	m7	m8	m9	m10			Estimation Type
					Analysis					NEW
1	Catalog Analysis,Prototype Analysis 1. Simple : 40 Hours 2 Medium : 64 Hours 3. Complex : 80 Hours	Medium					64.00	8.00	0.40					64.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
2	Catalog Translation 1. Simple : 16 Hours 2 Medium : 24 Hours 3. Complex : 32 Hours	Medium					24.00	3.00	0.15					24.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
3	Design Document preparation	1					32.00	4.00	0.20					32.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
4	Design Document review and Update	1					8.00	1.00	0.05					8.00	.00	.00	.00	.00	.00	.00	.00	.00	136
5	Estimation					8.00	1.00	0.05					8.00
					Development
6	Database table creation(For 50 fields)	4					6.00	0.75	0.04					6.00	.00	.00	.00	.00	.00	.00	.00	.00
7	Bring up screen and Layout (without business Logic)	1					5.00	0.63	0.03					5.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
8	Input framework (without business Logic)	1					4.00	0.50	0.03					4.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
9	Button (without business Logic)	15					7.50	0.94	0.05					7.50	.00	.00	.00	.00	.00	.00	.00	.00	.00
10	Single Select (without business Logic)	20					10.00	1.25	0.06					10.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
11	WAP Tab implementation (without business Logic)					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
12	WAP Accordion (without business Logic)					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
13	WAP Inbox Component (without business Logic)					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
14	Sima Grid-static(10 fields) (without business Logic)	5					15.00	1.88	0.09					15.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
15	Sima Grid -dynamic (without business Logic)	5					30.00	3.75	0.19					30.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
16	Magic Input (without business Logic)					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
17	Magic Import (without business Logic)					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
18	Elastic search (without business Logic)					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
19	Master Input (without business Logic)	10					20.00	2.50	0.13					20.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
20	Magic Paste(10 fields) (without business Logic)					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
21	Auto complete editor (without business Logic)					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
22	Faceted Navigation (without business Logic)					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
23	Insta Report (without business Logic)					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
24	File upload (without business Logic)					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
25	Comment container (without business Logic)					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
26	Other WAP components (without business Logic)	80					40.00	5.00	0.25					40.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
27	Server side check (10 fields)	3					3.00	0.38	0.02					3.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
28	Toaster					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
29	Approval Flow Implementation					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
30	Access Webapi					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
31	Service Setting Implementation 1. 1-100 Fields :Simple 2. 100-200 Fields :Medium 3. 200< Fields :Complex	Simple					8.00	1.00	0.05					8.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
32	First Time Component(New Component)	2					16.00	2.00	0.10					16.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
33	Special Logic Involved	40					40.00	5.00	0.25					40.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
34	META DATA entries ( 10fields)	3					1.50	0.19	0.01					1.50	.00	.00	.00	.00	.00	.00	.00	.00	.00
35	Test Data preparation	1					8.00	1.00	0.05					8.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
36	Business Logic Implementation (Development) 100% of component					131.50	16.44	0.82	131.5				131.50	.00	.00	.00	.00	.00	.00	.00	.00	.00
37	First Time Development 1-No : 0 hrs, 2-YES : 20% of Development)	YES	NO	NO	NO	NO	NO	NO	NO	NO	69.10	8.64	0.43	263				69.10	.00	.00	.00	.00	.00	.00	.00	.00	.00
38	Scenario video					0.00	0.00	0.00					.00
39
40	Unit Testing					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00
41					Review					.00
42	Code Review					16.00	2.00	0.10					16.00	.00	.00	.00	.00	.00	.00	.00	.00
43					Testing					.00
44	Catalog Analysis and Test case preparation					40.00	5.00	0.25					40.00	.00	.00	.00	.00	.00	.00	.00	.00
45	Chennai Hyouka 30% of Overall Development (Test Case Execution)					103.65	12.96	0.65	103.65				103.65	.00	.00	.00	.00	.00	.00	.00	.00	143.65
46	Bug fixing					103.65	12.96	0.65					.00	.00	.00	.00	.00	.00	.00	.00
36	0					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
37	0					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
38	0					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
39	0					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
40	0					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
41	0					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
42	0					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
43	0					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
44	0					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
45	0					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
46	0					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
47	0					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
48	0					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
49	0					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
50	0					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
51	0					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
52	0					0.00	0.00	0.00
53	0					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
54	0					0.00	0.00	0.00					.00	.00	.00	.00	.00	.00	.00	.00	.00	.00
55	0					#DIV/0!	#DIV/0!	#DIV/0!					#DIV/0!	#DIV/0!	#DIV/0!	#DIV/0!	#DIV/0!	#DIV/0!	#DIV/0!	#DIV/0!	#DIV/0!	#DIV/0!
56	0					#DIV/0!	#DIV/0!	#DIV/0!					#DIV/0!	#DIV/0!	#DIV/0!	#DIV/0!	#DIV/0!	#DIV/0!	#DIV/0!	#DIV/0!	#DIV/0!	#DIV/0!
	Total					813.90	101.74	5.09					710.25	.00	.00	.00	.00	.00	.00	.00	.00	.00	710.25

## Reference
Work Schedule Sheet - Reference Schedule
S. No	Items	Hours	Description			Holidays
1	Catalog Analysis,Prototype Analysis / 1. Simple : 40 Hours / 2 Medium : 64 Hours / 3. Complex : 80 Hours	0.00	Analyze Screen Functions and Flow			01/01/2017
2	Catalog Translation / 1. Simple : 16 Hours / 2 Medium : 24 Hours / 3. Complex : 32 Hours	0.00	Translate the Catalog related / Documents			01/14/2017
3	Design Document preparation	32.00	Prepare design document / For the screen			01/16/2017
4	Design Document review and Update	8.00	Review the Design Document and / Fix the business related issue			01/26/2017
5	Database table creation(For 50 fields)	1.50	create tables for the screen and / review the table structure. / Create DTO and DAO related files and / Master Tables			04/14/2017
6	Bring up screen and Layout / (without business Logic)	5.00	Basic Entry for getting / screen(Menu icons,service), / XML design(without Components), / Controller.			05/01/2017
7	Input framework / (without business Logic)	4.00	Implement XML for input,confirm, / Finish page. Implement controller for / input framework and implement / All the Default methods, / Validator and resolver creation.			06/26/2017
8	Button / (without business Logic)	0.50	WAP Button implementation			08/15/2017
9	Single Select / (without business Logic)	0.50	Implementation of single select			08/25/2017
10	WAP Tab implementation / (without business Logic)	0.50	Implementation of WAP Tab			09/29/2017
11	WAP Accordion / (without business Logic)	0.50	Implementation of WAP Accordion			10/02/2017
12	WAP Inbox Component / (without business Logic)	4.00	Implementation of WAP Inbox list			10/18/2017
13	Sima Grid-static(10 fields) / (without business Logic)	3.00	Sima grid static design and loading the grid			12/25/2017
14	Sima Grid -dynamic / (without business Logic)	6.00	sima grid dynamic design and load
15	Magic Input / (without business Logic)	2.00	Implementation of / Magic input component
16	Magic Import / (without business Logic)	0.50	Implementation of / Magic import component
17	Elastic search / (without business Logic)	3.00	create Elastic search and / Type layout creation
18	Master Input / (without business Logic)	2.00	Implementation of / Master input component
19	Magic Paste(10 fields) / (without business Logic)	2.00	Implementation of / Magic paste component
20	Auto complete editor / (without business Logic)	1.00	Implementation of / Auto complete editor component
21	Faceted Navigation / (without business Logic)	3.00	Implementation of / Faceted navigation component
22	Insta Report / (without business Logic)	4.00	Implementation of / Insta Report component
23	File upload / (without business Logic)	1.00	Implementation of upload functionality
24	Comment container / (without business Logic)	0.10	Implementation of / Comment container Component
25	New Application	3.00	Implementation of New application / Component includes(buttons,sub items, / Properties)
26	Anchor list Component	2.00	Implementation of Anchor list / Component
27	Other WAP components / (without business Logic)	0.50	Implementation of other / WAP component / (not mentioned above)
28	Server side check (10 fields)	1.00	Implementation of server side validation
29	Toaster	0.50	Implementation of error message, / Toaster and pop-up
30	Approval Flow Implementation	8.00	Data creation and implement XML, / Controller for approval tray. / Implement listener service / And controller for approval flow.
31	Access Webapi	0.10	Accessing already implemented / Webapi project
32	Service Setting Implementation / 1. 1-100 Fields :Simple / 2. 100-200 Fields :Medium / 3. 200< Fields :Complex	0.00	Implementation of service setting
33	First Time Component(New Component)	8.00	R & D of new component and / Implementation
34	Special Logic Involved		different component and / Different functionality
35	META DATA entries ( 10fields)	0.50	screen component label / Meta data entries
36	Test Data preparation	8.00	preparation of Master table data
37	Business Logic Implementation (Development) / 100% of component	0.00	Time for implementation of / Screen functionality		Err:508		-16
38	First Time Development / 1-No : 0 hrs, / 2-YES : 20% of Development)	0.00	For first time screen developer				-16
39	Scenario video	4.00
40	Unit Testing	24.00
41	Code Review	16.00	Code review and code logic checking / And Identify the common functionality
42	Catalog Analysis and Test case preparation	40.00	Analyze Screen Functions / and Flow(Tester) and / Create Test case for the screen
43	Chennai Hyouka / 30% of Overall Development / (Test Case Execution)	0.00	Testing the screen and / raise the issues
44	support / (1Developer-support the Chennai Hyouka Bug fixing)	0.00	Fixing Chennai hyouka bugs
45	Estimation	8.00	Rough Estimation

49
50
51
52
53
54
55
56

## DateSchedule
IVTL_Commuting Costs (Employee Info)
S. No		Task		Man Days	Man Months	No.of / Developers	Delay / Days	Start Date	End Date					Estimation Type
1		Catalog and Design		17.00	0.85	1.00	0.00	06/12/2017	07/05/2017		17					NEW

S. No	Screen	Task	Checkpoint	Man Days	Man Months	No.of / Developers	Delay / Days	Start Date	End Date					Checkpoint Enddate / Visibility	Checkpoint Startdate / Visibility	Startdate	Enddate	Used Hours / Per screen	Testing / Start date	Testing / End date	Testing / ManDays	Used Hours / Per screen / (testing)	Start Date / (Checkpoint)	End Date / (Checkpoint)	Start Date / (Set Final Checkpoint / Date as CR Enddate)	End Date / (Set Final Checkpoint / Date as CR Enddate)	Checkpoint / Start date
1	Screen 1			51.83	2.59	3.00	0.00	07/06/2017	07/31/2017	07/31/17	18					0	0	06/07/2017	31/07/2017	2.20	02/08/2017	21/08/2017	12.96	7.65
2	Screen 2			0.00	0.00					07/31/17	0	12/30/1899					0	0	31/07/2017	31/07/2017	0.00	21/08/2017	21/08/2017	0.00	0.00
3	Screen 3			0.00	0.00					07/31/17	0					0	0	31/07/2017	31/07/2017	0.00	21/08/2017	21/08/2017	0.00	0.00
4	Screen 4			0.00	0.00					07/31/17	0					0	0	31/07/2017	31/07/2017	0.00	21/08/2017	21/08/2017	0.00	0.00
5	Screen 5			0.00	0.00					07/31/17	0					0	0	31/07/2017	31/07/2017	0.00	21/08/2017	21/08/2017	0.00	0.00
6	Screen 6			0.00	0.00					07/31/17	0					0	0	31/07/2017	31/07/2017	0.00	21/08/2017	21/08/2017	0.00	0.00
7	Screen 7			0.00	0.00					07/31/17	0					0	0	31/07/2017	31/07/2017	0.00	21/08/2017	21/08/2017	0.00	0.00
8	Screen 8			0.00	0.00					07/31/17	0					0	0	31/07/2017	31/07/2017	0.00	21/08/2017	21/08/2017	0.00	0.00
9	Screen 9			0.00	0.00					07/31/17	0					0	0	31/07/2017	31/07/2017	0.00	21/08/2017	21/08/2017	0.00	0.00
10	Screen 10			0.00	0.00					07/31/17	0					0	0	31/07/2017	31/07/2017	0.00	21/08/2017	21/08/2017	0.00	0.00
		Total		51.83	2.59			07/06/2017	07/31/2017					Total	0		06/07/2017	31/07/2017		02/08/2017	21/08/2017

S. No		Task		Man Days	Man Months	No.of / Developers	Delay / Days	Start Date	End Date
1		Unit Testing		0.00	0.00	1.00	0.00	07/31/2017	07/31/2017		0

2		Code Review		2.00	0.10	1.00	0.00	08/01/2017	08/02/2017		2

S. No		Task		Man Days				Start Date	End Date

S. No		Task	Checkpoint	Man Days	Man Months	No.of / Testers	Delay / Days	Start Date	End Date
1		Catalog Analysis and / Test case preparation		5.00	0.25	1.00	0.00	07/06/2017	07/12/2017		5
S. No	Screen	Task	Checkpoint	Man Days	Man Months	No.of / Testers	Delay / Days	Start Date	End Date					CH Startdate / (without checkpoint)	CH Enddate / (without checkpoint)	Find last / Checkpoint / Man days	Unit Testing / Start Date	Unit Testing / End Date	Reference for / CH start date	CH Start Date / Last checkpoint	Code Review / Start Date	Code Review / End Date	Unit test/ / Code Review / Start date
2	Screen 1	0		12.96	0.65	1.00	0.00	08/03/2017	08/30/2017					03/08/2017	22/08/2017	0	31/07/2017	31/07/2017	01/08/2017	02/08/2017	01/08/2017	02/08/2017	29/12/1899
	Screen 2	0		0.00	0.00
	Screen 3	0		0.00	0.00
	Screen 4	0		0.00	0.00
	Screen 5	0		0.00	0.00
	Screen 6	0	0	0.00	0.00
	Screen 7	0	0	0.00	0.00
	Screen 8	0	0	0.00	0.00
	Screen 9	0	0	0.00	0.00
	Screen 10	0	0	0.00	0.00					08/22/17
		Chennai – Hyouka		12.96	0.65					07/13/17
3		Support		12.96	0.65	1.00	0.00	08/03/2017	08/30/2017

		Overall Schedule		88.78	4.44			06/12/2017	08/30/2017	12/30/1899

Description		Overall Schedule		Name					Date
Prepared by Overall Schedule					YYYY/MM/DD
Reviewed by Overall Schedule					YYYY/MM/DD

No of Developer		3			No of Tester				1
S. No	Developer Name			Emp.Id	Tester Name				Emp.Id
1	XXXX			XXX	YYYY				YYY
2
3
4
5
6
7
8
9
10

## Exclusion And Reference
S. No	Comments	Reference ID	Responsible Person
1
2
3
4
5
6
7
8
9
10
11
12
13

## RevisionHistory
S. No	Version	Description of Change	Date	Changed By	Reviewed By
1	1.3	Spec change added	15/06/2016	Kaviyarasan S	Karthikeyan M
2	1.4	1.Unit testing is separated into a phase. / 2.Scenario video is included with development phase. / 3.Database table creation time is updated as 0.50 hrs for 50 fields. / 4.Checkpoint calculation added	27/06/2017	Kaviyarasan S	Karthikeyan M